## ProPack
Red9 ProPack Codebase : Changelog
Hints | PRO | Python Module | System / Class | Submitted | Type | Function | Issue / upgrade | Details | Rig Uplift
| PRO | metadata_pro | Pro_MetaRig | 2020-05-29 | Update | Dag Menus | New support for the Red9 PuppetRig controller tag setups, exposed the "proximity_visibility" item under the dag menus
| PRO | metadata_pro | Pro_MetaRig | 2020-05-28 | Update | get_connection_datamap | Changes to the get_connection_datamap in meta, in ctrl_only mode was still returning MetaSupportNode data! | This was bloating the cPicker edit menus and slowing the process down
| PRO | optimiser | MalwareScanner | 2020-04-20 | Update | HealthTests | Added new Malware HealthTest in light of Malware found. We worked with Autodesk on a global fix
| PRO | exporter | ExportManager | 2020-04-17 | Bug | Playblast tracking | The start and end times weren't getting passed into the camera trackers which was processing the entire timerange regardless of the loop ranges
| PRO | exporter | ExportManager | 2020-04-17 | Bug | Playblast UI | The QT UI was getting deleted and faining to be re-loaded when called from both the ExportUI and from the main menu bar
| PRO | animation | AnimationTransfer | 2020-04-17 | Feature | Pro_to_BND | The batch mode was broken by the previous comit, this patch fixes that issue | the internal transfer_object was getting cleared from memory to try and optimise the batching, but this wasn't getting re-initialized again correctly
| PRO | animation |  | 2020-04-17 | Feature | offset_skeleton_to_frm | New function for offsetting a skeletons animation so that it starts from a given frame. This wraps the new functionality in the animCurve_get_ranges calls
| PRO | animation | r9Anim | 2020-04-01 | Feature | loadAnim / mRig.loadAnimation | Major update to the r9Anim format. We now normalize all data and load it up against the current framerate regardless of the internal key times. This means that you can save an r9Anim at 30fps and successfully, and correctly load it onto a rig in a scene at ANY fps | There's an internal var, AnimMap.remap_fps that will mute this behaviour if you find issues.
| PRO | animation | r9Anim | 2020-03-23 | Update | load_r9anim_direct() | Changes to the management for this call, new respect_framerate arg added to force the r9anim framerate to the scene on load.
| PRO | metadata_pro | Pro_MetaRig | 2020-02-25 | Update | bake_rig | The bakeKeys call in mRig always used to delete statics, which was missleading, this is now off by default
| PRO | metadata_pro | Pro_MetaRig | 2020-02-20 | Update | _set_ikfk_switchdata() | Added yet more flexibility to the IKFK wiring systems. We can now modifiy the way the IKFK calls behave on a system basis via the new _set_ikfk_switchdata() call. This binds a dict of vars to the mSystem passed in which are then consumed when any of the IKFK functionality is called | Allows for changes to the core vars used in IKFK handling
| PRO | tools | rig_manager | 2020-02-22 | Feature | PuppetTools menu added | Added new menu to support the new IKFK system switching calls. These are only supported under fully wired Pro_MetaRig class systems | The new menu items allow a fully setup rig to switch between full IK and FK states in one hit
| PRO | tools | rig_manager | 2020-02-01 | Feature | mNode class picker added | New UI added that pops up when you first get to choose th type of mNode you're wiring a rig too. This is purely for better clarity of the available generic mNodes we use.
| PRO | exporter | Export_Playblast_options | 2020-01-28 | Feature | Playblast settings | Added better camera management for the Playblast calls, including new "Static Fit/FrameAll" option which does a single frame fit on the mRig nodes before playblasting. Liek the tracker options but doesn't run over time
| PRO | exporter | Export_Playblast_options | 2020-01-28 | Bug | Playblast settings | The Playblast settings weren't propagating correctly to the Export.settings file, this was only an issue when the Playblaster was called from the Browser calls
| PRO | browser | extensions | 2020-01-28 | Update | Export updates | All "PRO: Export >" functions in the Browser now have the P4_Manage flag wrapped into them. If the Browser itself has the checkbox set then that will now propagate to the export calls. | This functionality was previously only available in the Exporter UI itself
| PRO | animation | AnimationTransfer | 2020-01-28 | Bug | Pro_to_BND | The batch mode was broken by the previous comit, this patch fixes that issue | the internal transfer_object was getting cleared from memory to try and optimise the batching, but this wasn't getting re-initialized again correctly
!! | PRO | animation | AnimationTransfer | 2020-01-14 | Feature | Pro_to_BND | Added support for Maya Rig to Maya Rig binding both in the PRO_TO_BND UI and the base transfer class | This allows uyou to use maya file containing a PuppetRig animation as the source for the binder rather than just using FBX input data.
| PRO | metadata_pro | MetaRigExternal | 2019-12-28 | Update | Pro_MetaRig_External | added HIK_BND wire and isBound call moved to base class to expose the Remapping functions to all
| PRO | animation | AnimationTransfer | 2019-12-28 | Update | Pro_to_BND | Upgraded UI, logging improved when running in batch, timerange management corrections.
!! | PRO | animation | AnimationBinder | 2019-12-28 | NEW Tool | anim_binder module | AnimationBinder has been upgraded for ProPack, new binding structures with zero transforms at initial bind. Also finally added the Mrig marker required for the PRO_to_BND calls | Much improved binder methods and exposure to batch remap
| PRO | exporter | ExportManager | 2019-12-20 | Feature | bookmarks | Maya 2020 now exposes bookmarks and the exporter will now create, bind and syn these to the export loops in the UI, with the ui driving and setting the bookmarks up
| PRO | metadata_pro | ExportLooopNode | 2019-12-20 | Update | bookmark_ | Bookmark creation and management extended to the exportloop systems
| PRO | animation | AnimationTransfer | 2019-12-20 | Update | Pro_to_BND | New internal functionality that allows the incoming fbx data to be force loaded from a given frame ragrdless of the incoming data. This will be exposed to the UI in the next release once tested further
!! | PRO | ALL | ALL uis | 2019-11-22 | Update | Uis | All ProPack UI's will now scale correctly under all 4k scaling resolutions. We've also introduced setting to store the Uis last position and size. Also all UI's will now be restored on boot if they were opened when you shut Maya down | Massive UI cleanup and 4k push
| PRO | animation | r9Anim | 2019-10-22 | Update | r9Anim | r9Anim load in relative mode now supports "skip" in the UI and the main load call. This allows you to use the relative code but skip either the rotates or translates in the calculations | Exposed in the Red9 ProPack>Animation SaveLoad : r9Anim
| PRO | browser | extensions | 2019-10-22 | Update | Extension Path | The management of the extension file paths has been changed to now store paths relative to the current Red9 mount. This means that if you move the codebase the extension will still be found as long as it was within the codebase. | Allows for ClientCore based extension files in the resource folders to be dynamically mounted correctly. If a path is outside of the codebase then it'#s still stored as an absolute path.
!! | PRO | animation | AnimationTransfer | 2019-10-20 | NEW Tool | Pro_to_BND UI exposure | Pro to BND our animation reMapper system has been exposed outside of the Red9 Browser, allowing you to quickly rempa a single fbx file to a given binder without having to launch the browser | This is for single fbx file remapping, making interaction faster.
| PRO | animation | AnimationTransfer | 2019-10-07 | Update | Pro_to_BND | Two new options on bake addded "spine_fit" and "locomotion track". The spine fit runs our iterative SplineIK fit algorithm to better preserve the shape of the spine during the transfer. Locomotion tracker runs the code to track the locomotion ctrl automatically for you | Spine fitting was actually origibnally written for this purpose to enable better data integrity when passing data to and from MoBu. The locomotion tracker is required as HIK doesn't remap the reference jnt so this re-calculates the data for game situtions
| PRO | metadata_pro | Pro_MetaRig_Base | 2019-10-07 | Update | bake_rig | bake _rig now has a new args "whole_start" which is True by default. This does a floor(startfrm) on the timerantge to process to ensure that we're not baking on sub-frames | This was an issue for the Binder systems as we relied on the fbx data times and these would often be sub-frames depending on the framerates
| PRO | importexport | FBX | 2019-10-04 | Bug | FBX | FBX handler class has been tightend to manage Take info, passed into the unpdate, import and reference calls
| PRO | animation | AnimationTransfer | 2019-10-04 | Bug | Pro_to_BND | FBX referencing and import calls now properly set the take data to ensure animation loads up correctly regardless of the current state of the fbx systems | the reference call used to use thf file command but there was no management of the take info. In some instances no take data would be passed or loaded.
| PRO | metadata_pro | ExportLoopNode | 2019-10-03 | Update | self.illegal_start_name | There's always been a clamp on the fileNames verified by the exporter. Previously we prevented any export loop name starting with a numeric, this limitation has now been lifted | To re-introduce this you'd need to sub-class the ExportLoopNode mNode class and add this back into the __init__ self.illegal_start_name = ['_', '0', '1', '2', '3', '4', '5', '6', '7', '8', '9']
| PRO | animation | r9Anim | 2019-09-20 | Bug | AnimationStore UI, Anim_Redirect UI | The handling of the presets has been tightened, previously if you'd built a new preset in the StudioPack AnimUI hierarchy tab but deleted after Maya was closed then this would bail the ProPack Uis as they're looking to load the last used preset. | Logic updated, if the last used preset no longer exists we default to the current PROJECT_DATA.data.pose_basePreset
| PRO | animation | r9Anim | 2019-09-20 | Update | AnimationStore UI | The Animation postload UI now allows you to resolve invalid audio paths before load. These get mapped via a new function in importexport "resolve_path" | Allows you to properly resolve bad audio paths before loading
| PRO | metadata_pro | Pro_MetaRig_Base | 2019-09-20 | Update | animMap_restore_export_data animMap_restore_audio_data animMap_validate | updates to the way we handle the extraction and management of the animMap_restore functions. The validate call never used to build the internal times which it now does. The restore methods now properly return times as floats. The Mrig.loadAnimation call can also now take an already instantiated AnimMap() class to use rather than always reading from disc (new **kws: ANIMMAP) | These are all designed to tighten up the support for the r9Anim data flow
!! | PRO | r9Pro Core | r9Pro | 2019-08-18 | Update | globals, uibase, r9pro | r9Pro / r9co files and boot sequence modified to handle new licensing system. R9co format changed | Big update to all the r9Co setup and the r9Pro management internally
| PRO | r9Data | r9Data | 2019-08-18 | Bug | r9Data | Class handling tightened up as there was a leak in the code when the settings dicts were first being instantiated. Lots of internal code updates to make this a more solid codebase | Bug fix
| PRO | animation | Anim_Transfer | 2019-08-15 | Bug | Pro_to_BND | Bug fix for binder open and import calls which were failing under some circumstances
| PRO | browser | r9Anim | 2019-06-21 | Update | r9Anim format | Extended the r9Anim file handling in the browser, for triggering the exporter calls directly from the r9Anim data itself. | Allows for Playblasting, exporting, converting to Maya file etc.
| PRO | animation | r9anim_browser_actions | 2019-06-21 | Update | r9anim_browser_actions | Added base wrapper to deal with r9Anims in the Browser, and to expose a very fast way to convert them into other formats | direct convert to mayafile, fbx or run a playblast off against them
| PRO | metadata_pro | getNodes | 2019-06-14 | Update | ExportTag_Base.getNodes | include_blends flag handling modified | it used to be that if the flag was on you'd get both blends and meshes regardless of the other flags. Now if just this flag is set you just get the blend data and the basejnts, not all meshes regardless
!! | PRO | metadata_pro | connection_datamap | 2019-06-14 | NEW Tool | save_connection_datamap load_connection_datamap | new functionality to enable us to save an entire mRig's node systems and all sub-systems out to file and recreate them on a fresh scene. This utilizes PRO_MetaRig.get_connection_datamap to build the data up which also means that 2 rigs can be compared as the wiring level! | This is designed to enable clients to build rigs through the RigManager and then rebuild them on other files
| PRO | project | project | 2019-06-01 | Bug | Project.p4_switch_client | The P4 switch client now also refreshes the internal p4_root var | This was causing issues with the p4+root path replacement when not running the switch through the ProjectManager
| PRO | importexport | resolve_path | 2019-05-20 | Update | resolve_path | new function to dynamically resolve bad paths. This will expand the filename existance search to either a given 'path_hint' list of folders, the Maya workspace mounts for the relevant filetype, or the current maya scene location. | This loosely mimics the Maya file handling, allowing paths to be corrected in code. Currently run in the r9Anim postload UI
!! | PRO | importexport | P4_SourceControl | 2019-05-20 | Update | r9ie.P4_sourceControl | The P4_SourceControl class P4 exception handler has been made public for better exposure self.__handle_exceptions is now self.handle_exceptions | Hopefully this exposes and makes the P4_SourceControl object more transparent to use
| PRO | browser | r9Anim | 2019-04-07 | Update | r9Anim format | Added multiple r9Anim file hanlding with the browser, for triggering the exporter calls directly from the r9Anim data itself. | Allows for Playblasting, exporting, converting to Maya file etc.
| PRO | browser | ReMapper | 2019-04-05 | Feature | Pro_To_BND | HIK support extended within the Pro_TO_BND functionality such that you can now add HIK property presets. | This enables us to initially do things like switch the remapping on mass to maintain contact points, or body shape.
| PRO | browser | ReMapper | 2019-04-02 | NEW Tool | Pro_To_BND | Pro_TO_BND now allows you to import, open or reference new data directly into an existing scene. | Previously the setup would only open the BND file and push the data to that in a fresh clean scene, but this was a limitation if you wanted to build a file up, from multiple FBX's onto multiple characters at the same time.
| PRO | exporter | ExportManager | 2019-03-15 | Feature | Set Custom Joint | the set custom joint UI has now be switched to a proper tree view to make things easier | Exposed in the ExportLoop UI only
| PRO | exporter | ExportManager | 2019-03-15 | Feature | Custom Export Path relative paths | Export Loop Custom export paths now support relative paths such as "../export" which will go out 1 folder form the current into a new subfolder called export | vastly extends the export path logic but is currently only availavble to be set in the ExportLoop UI directly
!! | PRO | exporter | ExportManager | 2019-03-15 | NEW Tool | Playblast support | Added Playblast support to the exporter - in Testing! | creates a plyablast in the same dir as the export per loop. Settings will be exposed soon
| PRO | exporter | ExportManager | 2019-03-11 | Feature | Custom Export Path | Added the ability to RMB set custom export path on mass to all selected loops. This overrides the default path resolve behaviour | Opens up a fileDialog for you to select the new path
| PRO | exporter | ExportManager | 2019-03-11 | Feature | Colour export loops added | Added the ability to RMB set colour for all selected loops in the UI, these can also be copy / pasted and are stored out in the r9Anim format so the colour is retained throughout the pipeline | This is a simple visual cue to organise tags
!! | PRO | animation | r9Anim | 2019-03-10 | NEW Tool | load_r9anim_direct() | r9Anim now supports direct loading IF it was saved from was an Mrig and that rig was originally referenced. This looks at the "info" data in the file and restores the original reference setup before then loading the data to it. | Exposed in the Maya>file menu and the Red9 Browser
| PRO | browser | Maya file open | 2019-03-10 | Bug | unsaved changes | In the browser when clicking the Maya>Open the code didn't used to check for unsaved scene changes. In now does and prompts as expected | Unsaved scene changes would get ignored
| PRO | browser | QT based UI | 2019-03-10 | Feature | Extension added | r9Anim extension support added which currently uses the new r9Anim direct load calls to expose loading of r9anims from file direct to the scene file. | see animation update "r9Anim Direct Load"
| PRO | tools | anim_tools | 2019-03-10 | Update | AnimCurve Filter | Butterworth filter now has a clamp ends function to maintain the first and last key selected
| PRO | metadata_pro | ImagePlane | 2019-02-28 | Feature | ImagePlane.timeOffset | timeOffset functionality added to the imageplane class so all tools in Red9 will now include imageplanes in there calculations
| PRO | animation | r9Anim | 2019-01-21 | Update | Load Relative Calculations | when loading in relative space the code wasn't projecting the space as expected. All offsets were in "absolute" space which gave inconsistent results if the reference object was rotated in all axis. This could result in the whole character animation being rotated at an arbitary angle | relative offset now uses the "projected" space similar to the PoseSaver's functionality
| PRO | audio | r9Audio | 2019-01-18 | Bug | timecode_maya_toggle_timeline( | Timecode toggle (cmds.animDisplay) args changed in Maya2018, causing this to bail. This is triggered when you RMB in the timeslider and run "Red9 PRO:Timecode: PRO : Toggle Timecode"
| PRO | animation | Anim_ReDirector | 2019-01-10 | Feature | Z up support | Addded support for Maya Z-up scenes in the reDirector, this was hard coded to Y-up built paths
| PRO | tools | rig_manager | 2019-01-10 | Feature | New Epic ART v1 support | Added new prest option to allow Epic ART v1 base rigs to be wired to ProPack in a single click in the top menu. More base systems coming soon | This setups up all the mirror handlers, the Pro_MetaRig nodes, filter priorities and everything needed to run. Only limitations are the IKFK switches won't work.
| PRO | exporter | ExportManager | 2019-01-08 | Feature | FrameRate validations | Because the start and end times are set agains a given Maya scene, if the framerate should change then this has never been reflected in the loop times. New Health test aded to the UI that compares the stored framerate against the current Maya unit and prompts to auto-fix the current loop timings for you | This is a simple health test added to r9opt along with a new framerate attr added to the ExportLoop class
| PRO | metadata_pro | ImagePlane | 2019-01-08 | Feature | ImagePlane | New ImagePlane MetaClass for handling and loading imagePlanes correctly in Maya
| PRO | animation | r9Anim | 2019-01-07 | Feature | Imageplane support | ImagePlane support has now been added to the r9Anim handlers, currently limited to just Facial rigs bound to the Pro_MetaRig_FacilUI class. | Stores and restores imageplane data with the r9anim file |  | Bug | New Tool
| PRO | animation | Anim_ReDirector | 2018-11-28 | Feature | Live Mode Added | New feature that allows you to interactively modify the re-direct path with the live data bound to it, changing the animation live rather than having to apply the cache to see the results. | Allows for massively more control of the re-direct data itself, you can even key the control clusters if needed |  | Feature | Update
| PRO | animation | Anim_ReDirector | 2018-11-24 | Feature | Smart Bake Added | New functionality similar to the r9Anim calls. The SmartBake function maintains current key keys on the objects during the remapping of the world space. Added for cartoon / parse baked sequences | Allows key times to be maintained when loading relative
| PRO | animation | r9Anim | 2018-11-21 | Feature | Smart Bake on load relative | New functionality when loading data "relative to" another object. The SmartBake function maintains current key keys on the objects during the remapping of the world space. Added for cartoon / parse baked sequences | Allows key times to be maintained when loading relative
| PRO | animation | r9Anim | 2018-11-21 | Update | Updated UI | New settings object added so all the flags are stored between sessions. UI also re-organised
| PRO | animation | r9Anim | 2018-11-21 | Feature | Mrig Load handler | New UI added to the r9Anim loader, activated if the mRig PreLoadUI checkbox is on, this opens when you set the r9Anim path and shows you all the export loops and audio data in the r9Anim, allowing you to pick what's restored | Added to expand capabilities and mRig handling of data
| PRO | metadata_pro | Pro_MetaRig | 2018-11-21 | Feature | mRig.LoadAnimation | New SmartBake flags exposed from the AnimationMap / r9Anim handlers
| PRO | exporter | ExportManager | 2018-11-15 | Feature | UI update | RMB Popup extend to support offset of ranges
| PRO | exporter | ExportManager | 2018-11-13 | Update | ExportUI | Refresh now maintains previous tag selection
| PRO | metadata_pro | Pro_MetaRig | 2018-11-13 | Bug | ExportLoop.timeOffset | When padding or collapsing time the start and end of the exportLoops are now taken into account in the base mNode.timeOffset() call (timerange arg is now propagated and dealt with correctly) | Previously if you added padding (rmb Red9 Insert Padding in the timeslider) at frame 15 and had an export range between 0 - 30, it would offset both values. Now it deals correctly with that pad.
| PRO | animation | Anim_ReDirector | 2018-11-12 | Update | Updated UI | Better handling added for switching between simple and path based re-direction. Sync Cloud now automatically blends back to the original data regardless of any path adjustments already done
| PRO | browser | QT based UI | 2018-11-10 | Feature | Extension Manager | new support added so that we can merge in given r9ext files with the default base ProPack's rather than them being exclusive
| PRO | audio | Timecode | 2018-10-10 | Bug | getTimecode_bounds | The main getBounds call was NOT taking the "ref" attribute into account when scanning, only the "count" was being used to ID tiemcode cuts on a node | Now scans both attributes on a given node for a more accurate picture of timecode cuts on a node
| PRO | audio | Timecode | 2018-10-10 | Update | Timecode.addTimecode_to_node( | New flag added that by default includes the current time in the initial calculations of timecode, if False we fully respect the start and end times passed in
| PRO | audio | AudioGRP_Manager | 2018-10-10 | Update | Filepath | The Audio Manager will now NOT allow you to connect audio to an mNode if the filepath of that audio contains Non-Standard ASCII characters | This prevents issues further in the pipeline, ensuring bad filenames do not get into production
| PRO | tools | rig_manager | 2018-10-08 | Feature | New External mRig wiring support | New systems added to properly enable users to wire up any rig to either a new pro_mrig_external mNode or pro_mrig_facialUI node. These are custom classes designed to mimic our internal Red9 PuppetRig setups more closely
| PRO | exporter | ExportManager | 2018-09-19 | Update | fbx handling | New flags added for better FBX support in the export process
| PRO | project | project | 2018-09-12 | Feature | Project Manager hooks | Added hooks that will dynamically bind keys in the project file with the naming convention "healthclass_????" directly to the actual HealthValidation lcass (if found and imported) This enables us to dynamically change some of the core functionality between projects on the fly | Enables massive flexibility for coders wanting to use the health classes
| PRO | project | project | 2018-08-30 | Feature | Perforce hooks | More hooks added to the project handlers and the ProjectManager to allow you to force over-ride the P4 status of a project dynamically | New checkbox exposed in the manager to enable this
!! | PRO | importexport | P4_SourceControl | 2018-08-22 | Update | r9ie.P4_sourceControl | The P4_SourceControl class now manages the P4 connection directly, also now exposing recent P4 connections via the connection_map() func. All previous PROJECT_DATA.p4 calls are still valid and the actual P4_API mapping is still directly bound to the PROJECT_DATA object. | Hopefully this exposes and makes the P4_SourceControl object more transparent to use
| PRO | project | project | 2018-08-22 | Feature | Project Manager | Massive uplift to the codebase and management to expose Perforce Server Management to the systems. This allows you to specify specific P4 server connections per client as well as picking the relevant workspaces mapped to each server | Perforce server connections managed
| PRO | r9cpicker | cpicker | 2018-08-22 | Update | Optimizations | Speed fixes in the way the data is managed to speed up the interface
!! | PRO | animation | r9Anim | 2018-07-04 | Bug | Incorrect tangent indexes loaded! | The tangent data is always loaded against a given index, not a given time and the previous implementation wasn't added any offset to those indexes if you were loading on a sequence with current keys! | We now resolve the index against the timearray used to create the keys in the first place to ensure we load the tangemnt data against the correct key!
!! | PRO | tools | anim_tools | 2018-06-18 | New Tool | SpaceMatchingUI | New Parent Space management UI for switching the parent space of the ik systems on the fly with full compensation | Available in the DAG menus and the main ProPack menu
| PRO | metadata_pro | Pro_MetaRig | 2018-06-17 | Update | switch_attr_compensated - code | Fixes to the time management and new "smartBake" and "step" frame args added
| PRO | exporter | ExportManager | 2018-06-13 | Bug | resolvedPath | If Maya throws an error on load it DOESN'T fill in the sceneName so we've had to by-pass the issue through the API to get a functional scenePath back
| PRO | metadata_pro | Pro_MetaRig | 2018-06-13 | Feature | ik_fk_match - step | Added new Step frame support to the IKFK matching calls | previously this only ran as a full frame bake
!! | PRO | metadata_pro | Pro_MetaRig | 2018-06-13 | Feature | ik_fk_match - ik spine resolver | New Spine IK iterative resolver added to do a "best fit" on the ik spine against the fk. This pins the chest ctonroller know- matter what the FK was doing and runs the best fit on the midCtrl to match the mid spine as best as possible | enables far more accurate IK results
!! | PRO | tools | anim_tools | 2018-06-13 | Feature | LimbMatcherUI | Moved the LimbMatcherUI class from animation to anim_tools and renamed to IK_FK_MatchingUI. Added ne "smartBake" and "step" frame support
| PRO | r9cpicker | cpicker | 2018-06-10 | Update | Callback Management | fixes to the way the callbacks were being managed
| PRO | exporter | ExportManager | 2018-06-05 | Feature | Scene callbacks | Added scene callbacks so if you open, import or reference anything and have the UI open then the tagss get automatically refreshed | Saves having to always hit refresh to re-scan the scene for tags
!! | PRO | project | project | 2018-06-01 | Feature | Project Manager | Support added for multiple projects per client under the same resource folder. Client.__init__ call project.load_project(projectfile) now replaced with a lighter wrapper project.add_project(projectfile) that just adds the project for later loading if needed. There can now be multiple add_project calls under the same __init__, adding multiple internal projects for a given client | Big speedups on load if multiple projects found. Better sync handling and expanded multi project support
| PRO | animation | Anim_Transfer | 2018-05-30 | Feature | rig_to_fbx | bake call replaced for a quicker option
!! | PRO | exporter | ExportManager | 2018-05-30 | Feature | FBX Settings added | New FBX settings handler added that supports the SceneRoot system, allowing the world co-ordinates to be reset per export loop. | This allows you to both drag data back to the world and compensate the world rotations. It also allows each loop to be auto-matically dragged back to world origin based on the Rigs CTRL_Locomotion controller, this then becomeing effectively the export/fbx world root.
| PRO | animation | Anim_Transfer | 2018-05-24 | Feature | rig_to_fbx | now takes additional "scale" flag to pass any scales through to the output skeleton data. Also added 'export_skl' flag to enable a skeleton to be passes directly in for processing
| PRO | r9cpicker | cpicker | 2018-05-22 | Update | Docking and Workspaces | fixes to the workspaces management between Maya versions
| PRO | exporter | ExportManager | 2018-05-20 | Update | setLoopName | Loops now can't start with "_", or any numerics | base code in metadata_pro.ExportLoop
| PRO | exporter | ExportManager | 2018-05-17 | Bug |  | Export loops setup by the r9Anim call were getting incorrect data set to the specificExportPath attr which in turn was invalidating the export path built
| PRO | exporter | ExportManager | 2018-05-17 | Feature | ExporterUI updated | New feedbacck added to the selection of loops in teh ui, we now automatically resolve and display the final output path. | ExporterUI updated
| PRO | exporter | ExportManager | 2018-05-17 | Feature | Ui and code updated | New Exposure of the Specific Path handling in the LoopTag UI so that you can set an over-ride output path at the Tag level OR the Loop level | Ui and code updated
| PRO | r9cpicker | cpicker | 2018-05-17 | Bug |  | the UI is docked in a Workspace and this wasn't sending the close command to the callbacks which were always running even if the UI were closed | Workspace control now handled correctly and the callbacks killed on close
| PRO | r9cpicker | cpicker | 2018-05-17 | Update |  | The cpviews data has always been stored in the main cpicker attr on the mNode but this was forcing changes to the base data. This is now a separate cached block of data on the mNode so the original cpicker attr is never touched, unless in Edit Mode | Done for consistency and data handling
| PRO | metadata_pro | Pro_MetaRig | 2018-05-16 | Feature | ik_fk_match - autoclav solver | New Auto-Clav handler added to the ik>fk switch calls, also exposed as a new bake option in the DAG menus | previously when switching from IK to FK the Autoclav was driven off and no matching attempted
| PRO | browser | QT based UI | 2018-05-10 | Bug | Perforce fixes | double file entries in P4 mode - depending on the clients P4 woprkspace setup we were getting double entries in the UI | Path handlers made more robust
| PRO | project | project | 2018-05-10 | Bug | Project Manager | Instance where P4.info was returning *unknown* for user info has been by-passed. | Seems like this is a server side issue but we can't find any more info, simply using p4.user rather than the info call retunrs the correct data
| PRO | project | project | 2018-05-10 | Bug | Project Manager | Expired P4 session will fail ProjectManager | If the P4 session times out then this was bailing the feedback in the UI and preventing it from launching
!! | PRO | audio | Red9 Sound | 2018-05-05 | Feature | Red9 Sound | Main Red9 Sound Menu has been added to the main Red9 menu so it's available outside of the TraxEditor
!! | PRO | devkit | devkit | 2018-04-13 | Feature | New Editor auto-complete stubs | Because r9Pro files are compiled you currently get no auto-completion in your editors when coding around it. That's now been fixed | All you need to do is to add the pro_pack.devkit.completion path to your editors interpreter and you'll now get full completion when using Red9 ProPack
| PRO | tools | rig_manager | 2018-04-08 | Feature | Better support for client custom rigs | Added new logic to allow clients to quickly marker up their own rigs by hi-jacking the SRC manager tab
| PRO | browser | QT based UI | 2018-03-20 | Feature | Perforce integration | When running a Project object that points to Perforce we now add Perforce support to the Browser UI. This means you can scan Perforce directly as a file system inside the Red9 Browser | Allows fast interaction from within Maya directly to Perforce files, shows you what you have, what's out of date, what missing and what needs adding etc
| PRO | metadata_pro | Pro_MetaRig | 2018-02-23 | Feature | anim_point_cloud - code | Added direct exposure of the animPointCloud to the Pro_MetaRig so that we can use it to transpose world space on the fly | this isn't yet exposed except in code but is a really key function to allow us to change data on the fly without it effecting the rigs pose
| PRO | metadata_pro | Pro_MetaRig | 2018-02-23 | Feature | switch_attr_compensated - code | a wrapper over the anim_point_cloud, allowing an attribute on a node to be changed whilst compensating for that change in the rigs transforms | this will eventually be exposed to allow us to change Parent spaces on the fly, both static and over time
| PRO | metadata_pro | Pro_MetaRig | 2018-02-23 | Update | ik_fk_match, fk_ik_match | new timerange flag added to allow us to directly pass in the timerange to process | previously time was just a bool which triggered a get of the current timeline bounds only
!! | PRO | importexport | SOURCE_CONTROL | 2018-01-10 | Update | r9ie.P4_sourceControl | Massive update to the P4 handling and how we're wrapping it. All previous property's have been turned back to functions for speed in the Maya scriptEditor. Lots of additional logic in the hadnling added for better debuging and stability in the connection. | This is TOTALLY dependent on the PROJECT_DATA object's P4 bindings
| PRO | metadata_pro | Pro_MetaRig | 2018-01-10 | Update | Pro_MetaRig | fk_ik_match and methods for resolving the ik and fk chains have been uplifted | ikimatchpnt now has a pointer to the controller it relates too, these used to be hard-coded. New method for matching the toe data added which relies on a new patch.
| PRO | optimiser | New HealthTest | 2018-01-10 | Update | P4_sourceControl | ALL Properties converted back to function calls | With some of the Perforce calls being properties it was massively slowing down code completion in Maya, all properties in the current P4 bindings have been removed, things like .fstat will now need to be called as functions .fstat()
| PRO | project | project | 2018-01-10 | Feature | Project Manager | New Project call "p4_switch_streams" which now allows you to dynamically change the current P4 stream/client mount. | Really useful if you have P4 setup with multiple mounts/clients in the same workspace
| PRO | metadata_pro | Pro_MetaRig | 2017-12-11 | Feature | Pro_MetaRig_FacialUI | BIG update to this base facial class to support custom modelPanel views, camera creation and alignment, imageplane management and a new head_instancer call to allow you to draw front, side_left and side_right in the viewports | This all relies on the mClass node being wired to the head meshes via the "renderMeshes" wire on the class
| PRO | tools | anim_tools | 2017-11-08 | Feature | Simple Mode in r9Anim | Simple mode now added to the AnimationStore | switches to base hierarchy mode to make it easier to handle simple hierarchy node structures
| PRO | animation | r9Anim | 2017-10-30 | Bug | Incorrect global tangent types | The code has always used the OpenMayaAnim.MFnAnimCurve.kTangentGlobal when first setting up the tangents, this causes issues if not set to auto or spline due to some of the internal optimizations | Loader now uses "auto" as the default tangent type and works from there. This is only a LOAD bug, doesn't affect the save call or any current data
| PRO | animation | r9Anim / ReDirector | 2017-10-15 | Feature | Added Settings Button | Added settings button to both the AnimSaver and Anim ReDirector Uis that now opens up the Hierarchy Tab in the AnimToolkit | This should make it more obvious that the presets are all tied together
| PRO | animation | r9Anim | 2017-10-05 | Feature | Insert / Merge | Added support for PasteKey methods | Now allows you to either "insert" or "merge" the new keys being loaded into the nodes current animCurve data
| PRO | tools | anim_tools | 2017-10-05 | Feature | Tangent management | added tangent management to the Butterworth filter | Butterworth filter code now allows you to set the tangent type used in the UI
| PRO | install setup | module | 2017-10-01 | Install | File Changes | Modified the structures to be booted as a Maya module by default
| PRO | animation | r9Anim | 2017-09-18 | Bug | Maya Units | The API load code wasn't dealing with unit conversion so units in meters were being loaded in centimeters. | Handling added for all unikt conversions, this uses the sceneUnits stored in the file to convert all linear units.
| PRO | metadata_pro | Pro_MetaRig | 2017-09-15 | Feature | parallel_eval_mute/reset | new management for parallel eval optimisations | This sets the frozen attr state on all nodes returned by the parallel_eval_get_nodes fun, designed to be overloaded as needed.
| PRO | animation | parallel support | 2017-09-05 | Feature | playback_performance, parallel_eval_freeze, parallel_eval_unfreeze_all | wrap over the eval Manager 'frozen' node state to stop node evaluating in parallel mode and added performance tester | Used to speed up rigs under certain cases and performance test
| PRO | metadata_pro | Pro_MetaRig | 2017-06-23 | Bug | _get_fk_chain | On certain systems was returning the fk chain in the incorrect roder | This is now patched, fixing issues in some of the fk>ik sytem calls (seen primarily on the Puppet rigs head system)
| PRO | exporter | ExportManager | 2017-06-08 | Feature |  | Full timecode support added in the RBM menus so that you can stamp timecode against a given shot / loop | Very useful if you want to uise the dynamic timecode in the TimeCode UI to match audio data to multiple timecode slices in the same scene
| PRO | animation | r9Anim | 2017-05-12 | Feature | r9Anim format | Big optimization and a lot of the core code moved to the API which vastly improved load speeds | In our test file a dense baked mocap sequence of 1500 frms went from 45 secs to just 8!
| PRO | audio | Timecode general | 2017-05-05 | Feature | dynamic timecode added | Timecode has up to now been a single linear time, now we add in support for dynamic, multiple timecode zones in the same scene / rig | This allows us to stamp multiple time bounds to a rig (via the RMB SetTimecode Range in the exporter) and have bwavs automatically scan through all of the bounds to find an appropriate one to sync to
| PRO | exporter | QT based UI | 2017-05-05 | Update |  | UI uplift including the ability to lock the ranges in the UI, set Maya playback to mutiple ranges, and sort the ranges by name, loop or expTag | UI Update
| PRO | animation | r9Anim | 2017-04-14 | Bug | animtaion_Store/Load UI | Seems like PySide2 has issues with error handling, resulting in the UI freezing on us if a connected signal caused an error. In PySide this would just print ther error out to the script editor, but in 2017 it hands the application! | try excpets and error handling added to all the feedback calls to prevent this happening
| PRO | project | project | 2017-03-23 | Feature | Project Manager | New Project Setup button added to the Maya toolbox | Allows better control of multiple projects, shows via an icon what current project is booted and acts as a fast link to the new Project_Manager UI and switch project function
| PRO | metadata_pro | Pro_MetaRig | 2017-03-22 | Feature | trax_makeclip | Added call to create a Trax clip from the given mRig's animation
| PRO | r9pro | License | 2017-03-22 | Install | File Changes | Red9 R9USER License file system and r9Settings have all been moved into the maya prefs dir as we were finding that windows system optimizers would delete the R9PRO folder from the users temp dir. All r9Settings files will now be stored in a single user folder under prefs, seperating them from the build folders | RED9_LICENSE_LOCATION=PRO_PREFS , PREFS, BUILD or TEMP where internally the PRO_PREFS is now default
| PRO | project | project | 2017-03-17 | NEW Tool | Project Manager | New Project Manager UI to allow for multiple teams and multiple projects to be switchable, changing the loaded project template and propagating that | Allows better control of multiple projects / clients
| PRO | r9cpicker | cpicker | 2017-03-15 | Update |  | BG images for the cPicker will now try and use the Project resource folder before lookingin the picker dir | This means that each clients resources are kept clean and separate!
| PRO | exporter | ExportManager | 2017-03-08 | Feature |  | Added new Shot Info handling both in the UI and at the base exportLoop level. This data also propagates via the gatherInfo command so it caught and stored in the r9Anim files also
| PRO | animation | Pro_To_BND | 2017-03-03 | Feature | animtaion_transfer | FBX files that aren't skeleton compatable with our BND file can now load via the HIK plugs | Added a new method "connect_hik" for dealing with the load and transfer of FBX data, added new option menu in the Pro_TO_BND UI to switch to the new behaviour.
| PRO | metadata_pro | Pro_MetaRig | 2017-03-01 | Feature | bake_rig | Added direct bake call into the class which not only allows you to bake the entire rig, but also manages the Red9 Binder system too
| PRO | tools | HealthManager | 2017-02-15 | NEW Tool | New HealthManager | First build of the new Health Manager system
| PRO | install setup |  | 2017-02-14 | Install | File Changes | Replaced setup.r9settings for setup.r9config | This is so that when submitting new builds to P4 we can get clients to make an exception that r9Settings files in general do not get submitted
| PRO | install setup |  | 2017-02-14 | Install | File Changes | Removed depricated projectconfig module | This was a test and we never actually used it, replaced with the Project object
| PRO | metadata_pro | ik fk management | 2017-02-06 | Update | fk_ik systems | New management of the ik fk systems to make it more flexible for other clients rigs. | add_fkik_matchpnt - new function to add in a managed IK match pnt dynamically. New functions for _get_ik_chain and _get_fk_chain in the Pro_MetaRig class so we can modify the extraction of these chains for different setups. The data is passed directly to the fk matching systems
| PRO | animation | Pro_To_BND | 2017-01-26 | Bug | animtaion_transfer | FBX files with namespaces failed to load onto binder files | Added a new method "reference_copy" for dealing with the load and transfer of FBX data, added new option menu in the Pro_TO_BND UI to switch to the new behaviour.
| PRO | metadata_pro | Pro_MetaRig_Base | 2017-01-23 | Update | visibility_ calls | All visibility calls now take an additional 'toggle' arg so you can just toggle the state of the call in one easy step
| PRO | metadata_pro | Pro_MetaRig | 2017-01-20 | Feature | poseLoad_blended | Added in a new function for easily blending in the given pose directly from mRig, brings up a floatslider to dial in the value unless percentage is given as an arg
| PRO | audio | Timecode general | 2017-01-15 | Feature | timecode maya production | Time sync using Maya Production Timecode | Added integration for the Maya Production Timecode in the timeline as a new set of options. Allows you to use this in a user freindly way, mapping the timecode sen in the timeline.
| PRO | r9cpicker | cpicker | 2017-01-14 | Bug |  | FK-IK switches on the picker were not in sync with the state of the rig on load | New sync function added so that the state of the FKIK switches on the default template will sync to the state of the rig on load, also added a refresh button for this
| PRO | audio | Timecode_Wrangler | 2017-01-10 | Feature |  | Added new Timecode Wrangler / AudioOffset Manager and removed Timecode Bwav functions from the StudioPack offsetManager
| PRO | optimiser | HealthValidation | 2017-01-10 | Bug | run_fix_methods | The order of the fix methods run was NOT reflective of the order of the tests that were passed in | Fixes and test order now tracked and maintained
| PRO | project | project | 2017-01-10 | Bug | ClientBoot | All Client __init__ calls modified as the PROJECT_DATA binding now HAS to be at the head of the init file so that the Project data is up for all other functions to use | Fixes the boot issues with source_control bindings
| PRO | project | project | 2017-01-05 | Update | switch_client | PROJECT_DATA.switch_client() added to switch the data bound on hte fly to any available client listed in the PROJECT_DATA.projects_available dict
| PRO | importexport | SOURCE_CONTROL | 2016-12-30 | Bug |  | r9ie.SOURCE_CONTROL var removed, all source control queries now go via the PROJECT_DATA.source_control() call which manages multiple projects and caches the data for speed
| PRO | importexport | SOURCE_CONTROL | 2016-12-30 | Bug |  | r9ie.SOURCE_CONTROL var removed, all source control queries now go via the PROJECT_DATA.source_control() call which manages multiple projects and caches the data for speed
| PRO | project | project | 2016-12-30 | Bug | P4 / boot managment | huge restructure to speed up boot times when dealing with Perforce. Added in a lot of secondary management for soucre_control and the p4_root+ path marker now also works on sub-level paths in dics, such as the binder path dict. | Perforce based projects would vastly increase boot time IF P4 was not connected. The code ised to ping P4 multiple times.
| PRO | metadata_pro | Pro_MetaRig | 2016-12-28 | Update | FilterSettings | FilterSettings now getting bound internally to rig on publishing. This allows us to over-load any default filter configs and means that we can properly run the PoseCacheLoad relative correctly. | PoseCacheLoad "relative" now functioning correctly due to internal filterSettings data being bound to mNode on Publish | Puppet v1.06 and below
| PRO | metadata_pro | Pro_MetaRig_Base | 2016-12-22 | Feature | Dag Menus | DagMenu's : added IK>FK Match Over Time and FK MatchUI
| PRO | metadata_pro | Pro_MetaRig_Base | 2016-12-22 | Feature | Dag Menus | DagMenu's : added Pose management to the menus, caching the rig's state and able to load relatively | Rig uplift needed as Rigs need the internal Settings pushed to the mNode | Puppet v1.06 and below
| PRO | metadata_pro | Pro_MetaRig_Base | 2016-12-22 | Feature | Dag Menus | DagMenu's : Modified the Timecode management setups
| PRO | exporter | ExportManager | 2016-12-20 | Feature |  | Added a new option call - ExportManager.output_mayafile that saves out the current maya file but because its in the exporter class is P4 managed and name managed through the exportLoops
| PRO | metadata_pro | Pro_MetaRig | 2016-12-20 | Bug | FK>IK Matching | MetaRig Pro - fixes to the FK>IK matching management, now allows for match over time in the RMB dag menus
| PRO | animation | FK>IK Matching UI | 2016-12-16 | Update |  | Replaced cmd UI with new QT build
| PRO | metadata_pro | Pro_MetaRig_FacialUI | 2016-12-16 | Feature | ImagePlane | Added ImagePlane support to the Facial mRig base
| PRO | r9cpicker | cpicker | 2016-12-05 | Feature |  | Completely replaced the cPicker UI, this is now interactive, draggable, has live feedback on selections from the viewports, is faster and allows for more custom button and action management | Full system update - requiring new Picker data file to be bound to older rigs | Puppet v1.06 and below
| PRO | r9pro | License | 2016-12-01 | Install | File Changes | Red9 R9USER License file moved to the temp dir by default but there are Environment flags to modify this behaviour | RED9_LICENSE_LOCATION=PREFS or BUILD or DEFAULT which will re-direct the license to the maya prefs folder, or insode the ProPack build folder, or leave it in the temp folder. If you don't put this in the maya.env file then the licese will go to the default location
| PRO | tools | anim_tools | 2016-07-04 | Feature | SpaceMatchingUI + IK_FK_MatchingUI | Both now support post Euler filtering on the resulting data
| PRO | tools | anim_tools | 2016-04-28 | NEW Tool | New AnimCurve Filter | New advanced animation curve filter that introduces the Butterworth filter | Butterworth filter algorithm is one of the key tools in MotionBuilder for cleaning up dnese baked data so we've bought it into Maya ;)
| PRO | tools | rig_manager | 2016-04-08 | NEW Tool | New Rig Manager | New interface for managing the Red9 Puppet Rigging back-end to a certain degree
| PRO | tools | project_manager | 2016-03-22 | NEW Tool | New Project Manager | New Project Manager interface for better clarity of the back-end ProjectObject data

## StudioPack
Red9 StudioPack Codebase Changelog
Studio | Module | System / Class | Submitted |  | Function | Issue / upgrade | Details | Rig Uplift
SP | r9Anim | r9Anim | 2020-06-18 | Bug | MirrorHierarchy | The Mirror code _validateKeyedNodes call which keys static attrs when told to do so was forcing a key on ALL attrs on the offending nodes, not just the unkeyed attrs
SP | r9Meta | MetaRig | 2020-06-17 | Bug | poseCacheLoad | the poseCache setup extracts filterSettings data from the mRig node, but was failing to also set the filterPriority flag in the pose object meaning that ALL nodes were getting processed when using the load relative setups
SP | r9General | r9General | 2020-06-10 | Bug | AnimationContext | new management of the cached evaluation for Maya 2019 / 20. The lack of this was causing issues for a lot of the time based animation snap routines
SP | r9Pose | PoseData | 2020-04-29 | Update | skipAttrs | The skipAttrs var is now respected if passed into the Pose object |  |  | Feature | Update
SP | r9Meta | MetaClass | 2020-04-17 | Update | getAnimationRanges | now takes the new flags for the animCurve_get_bounds func
SP | r9Anim | r9Anim | 2020-04-17 | Update | animCurve_get_bounds | New handling for this key function. It now will return not just the animation key bounds (first key and last key). But also the actual range of the changing data. This works in from the start and ignores static keys. | Really useful in finding actual animation changes rather than just static data
SP | r9General | r9General | 2020-03-23 | Update | os_listFiles | this now takes a "filterString" arg which is the same as the rest of the regex based filters in r9 Core. Enables you to search for files under a folder with specific file name handling | this is great for pin-pointing files under a root folder
SP | r9Anim | r9Anim | 2020-02-27 | Bug | AnimationUI | When calling the MirrorAnim mode we now hard code the pasteKey method to 'replaceCompletely' which by-passes another mirror anim bug. The pasteKey method used to come from the CopyKeys options but that makes no sense in this instance. | Used to be that when mirroring data on left and right pairs that if one side only had a single static key, but the other had full range baked data, ONLY that single key would get swaped but it would effectiovely get merged into the previous sides data..... the frame after we'd get a pop. This solved this issue
SP | r9Anim | r9Anim | 2020-02-27 | Bug | MirrorHierarchy | New validation to check if nodes have no key data before we try and mirror in Anim Mode, if not we throw a prompt which allows you to set Keys on the offending attrs before the process. | This has always been an issue with the mirror anim mode, requiring all nodes to have key data. This new handling makes sure this is dealt with internally.
SP | r9General | r9General | 2020-01-14 | Update | readJson | readJson main command now throws a ValueError if the json file is incorrectly formatted
SP | r9Core | r9Core | 2019-12-20 | Update | LockChannels | LockChannels has had some logic tweaks when dealing with the compound rotate,tranlate and scale data. On load we were locking these by default, then running the unlocks, this was causing issues in certain cases.
SP | r9General | r9General | 2019-11-28 | Update | thumbnailApiFromView | Fixed the API call, issues with VP2. Also changed it so that the modelPanel is no longer hardcoded but an arg. If blank (default) we now detect the active modelPanel to use. | The wrap in the poseSaver has also been updated
SP | r9Anim | r9Anim | 2019-11-22 | Update | AnimUI | basePreset management fixed. | the idea of the basePreset was so that ProPack users could specify a default, "client" basePreset to inject into the AnimUI for new users. This mechanism was broken by changes in the workspace calls but never caught.
SP | ALL |  | 2019-11-22 | Update | all UI's | All UI's in StudioPack have had major work to make them more 4k compliant. All ui's now alo have a proper self.close() call to bring them in line iwth the QT builds
SP | r9Anim | r9Core | 2019-11-04 | Bug | Pose Path UI | If you manually edit the PosePath to an invalid, hit enter, then manually edit it back Maya crashes | Now validating the path before we fill in the ui data
SP | r9Meta | MetaClass | 2019-10-28 | Update | getChildMetaNodes | new flag added "currentSystem" designed to prevent the search from walking into child mRig systems. This uses the mSystsmeRoot checkbox as the hint | If True and we hot an mNode with teh mSystemRoot checkbox=True then we prevent the search from walking into that sub-system. Designed for child facial rigs
SP | r9Core | r9Core | 2019-10-28 | Update | TimeOffset | mRig logic improved to handle child mRig systems more consitently. If you have a facial system connected to a body system then both will get offset by default. New flag added to control thuis behaviour | TimeOffset.fromSelected(...... currentSystem) new flag. If True we clamp all mRig offsets to the current system and DO NOT deal with child sub-rig systems. Default=False
SP | r9Core | r9Core | 2019-10-28 | Update | TimeOffset | Main class now takes a new flag in the __init__(cache_object) This allows us to pass in a previous TimeOffects._processed list, ensuring no nodes are processed twice | This is primarily there to allow the mNode.timeOffset calls to be passed the list of processed nodes. Prior to this some of the functions madde a fresh instance of the TimeOffset class which by-passed this mechanism
SP | r9Meta | MetaClass | 2019-10-04 | Update | getMetaNodes | added new key, "byname" so you can pass in nodeName that you want the systems to instantiate / find
SP | r9Anim | r9Anim | 2019-09-25 | Bug | AnimationLayerContext | This wasn'tdealing with locked layers correctly | fixed
SP | r9Anim | r9Anim | 2019-09-05 | Update | AnimUI | modified all codebase to be more compliant with 4k setups
SP | r9Anim | r9Core | 2019-06-28 | Bug | TimeOffset | all TimeOffset calls now track whats been offset internally making sure that nothing should ever get passed into the handlers twice as was happening in some cases.
SP | r9Anim | r9Anim | 2019-06-21 | Bug | CameraTracker | This no longer forces a check to the optVar that sets the 'keepOffset' flag in the base call. This is only now checked by the UI itself
SP | r9Pose | PoseData | 2019-06-21 | Bug | _getTranforms | Crash / Maya hang bug tracked down to the euler convert call, this has been modified and seems to by-pass the issue
SP | r9Meta | MetaClass | 2019-06-14 | Update | gatherInfo, create_mNode_from_gatherInfo | Modified so that we now also have a low level call which all code shares. gathewrInfo_mNode. This is the block of code that produices just hte info needed to reconstruct this node using the new create_mNode_from_gatherInfo call | Why? This forms the mechanism in ProPack to store out a dict of all mNodes in the scene which can then be dynamically re-built from scratch before being wired
SP | r9Meta | MetaClass | 2019-06-14 | Update | getNodeConnections | new flag "bothplugs" that returns a list of tuples where with the names of the 2 connected attrs [mNodeAttr, srcAttr]
SP | r9Anim | r9Anim | 2019-06-04 | Update | getChannelBoxSelection | Added new flag to return the attribute longNames properly
SP | r9Meta | MetaClass | 2019-05-20 | Update | registerMClassNodeCache | Changed the way the metadata cache deals with the UUIDs. If a UUID is already registered in the cache but against a different mObject then we regenerate that UUID and re-enter it as a fresh entry to the cache | Under Maya referencing UUIDs are NOT unique!!
SP | r9Anim | r9Anim | 2019-05-01 | Feature | AnimUI | Added a new button to the Pose Tab for Blend loading of a pose. This was always on the RMB click menu but it's a key function so has been added directly to teh UI | The PoseBlending is particularly powerful when you're dealing with Facial data and calibrations!
SP | r9Meta | MetaClass | 2019-04-26 | Feature | MetaHIKPropertiesNode | Extended class to handle HIK property node, allows us to now store and load prests for this mapping data directly. | The file written out by this is what the Pro_TO_BND HIK support is looking for. If you want to make your own you need to copy your preset into the "pro_pack\resources\hik_presets"
SP | r9Core | r9Core | 2019-02-14 | Update | r9Core.matchNodeLists | added additional handling for metaData matching, by default when matching with metaData we compare mNodeID and mAttr for each node, but in some cases mNodeID on simple rigs may have been modified by users, failing the match | we now catch unmatched nodes and regress the matching to "stripPrefix" if this is the case, basically doing a second pass match on the data |  | Bug | New Tool
SP | r9Pose | PoseData | 2019-02-14 | Update | processPoseFile | added additional handling for metaData matching, by default when matching with metaData we compare mNodeID and mAttr for each node, but in some cases mNodeID on simple rigs may have been modified by users, failing the match | we now catch unmatched nodes and regress the matching to "stripPrefix" if this is the case, basically doing a second pass match on the data |  | Feature | Update
SP | r9Meta | MetaClass | 2019-02-10 | Update | MetaRig.mirror_delete_all_markers | added a base call to delete all mirrormarkers in one go from a given metaRig
SP | r9Meta | MetaClass | 2019-02-10 | Update | __getMessageAttr__ | this calls listConnections but that never had the "shape" flag set so if you have connected shape nodes to the mNode only the transform would come back. | Shape flag added and now returns shape node themselves if connected. Added for the imageplane support in ProPack
SP | r9Anim | MirrorHierarchy | 2019-01-22 | Feature |  | Mirror Setup UI now also supports custom channels which can be grabbed from the channelBox selection directly
SP | r9Core | r9Core | 2019-01-16 | Bug | r9Core.matchNodeLists | when using the stripPrefix method the code never actually did an initial name=name pass before relaxinig the search method. | We now do this, fixing issues where we may have several possible resolves in a heirarchy ie: "hip_ctrl", "LF_hip_ctrl", "RF_hip_ctrl" all of which would pass when matched against "hip_ctrl". The new initail base pass prevents this.
SP | r9Meta | MetaClass | 2019-01-05 | Update | __createnode__ | New call that's responsible for creating the node. This used to just be a cmds.createNode(nodeType) call in the __init__ but by exposing it as a function we can overload per class if needed
SP | r9Meta | MetaClass | 2019-01-05 | Update | __init__ | Changes that now allow you to create a node of ANY type regardless of it being registered in the RED9_META_REGISTERY. This is for speed if you want to use the call during a rig build for example | r9Meta.MetaClass(nodeType='multiDivide') will now return a standard wrapped MetaClass node whilst also creating the muliDivide node at the same time
SP | r9Meta | MetaClass | 2019-01-05 | Update | __new__ | Changes to the way that nodes are registered such that if there's a registered class who's name matches a Maya nodeType (thats registered) then the code will automatically return that class.... Assuming that the node doens't have an mClas attr already set | This was added so that imageplanes can be automatically returned in ProPack as a class without having to reply on them being created by a MetaClass, ie, they haven't got the mClass data and are still Maya native
SP | r9Core | r9Core | 2018-11-13 | Update | TimeOffset | Undo stack now properly handled as single undo | undoContext added to main functions
SP | r9Core | r9Core | 2018-11-13 | Update | TimeOffset | mNode handling improved | mNode.timeOffset function now called when doing selected timeoffset calls such as padding selected mRigs, previously this call was only made at the scene level
SP | r9Pose | PoseData | 2018-11-07 | Bug | loadPose | Previously if you had an attribute with clamped values and were trying to set the pose to values past these, the load would skip. We now set the values upto their max/min if this is the case | Now handled correctly by adding the clamp=True flag to the set Attr calls
SP | r9Audio | AudioNode | 2018-10-08 | Update | isValid | Now checks for non valid Ascii characters in the audio path name and fails if found | With invalid Ascii characters some of the other systems that store that path fail further down the line in the pipe
SP | r9General | ascii_sanitizer | 2018-10-08 | Feature | ascii_sanitizer | New function to return a valid string from invalid ascii characters, useful for sanitzing data before it's passed around
SP | r9Anim | r9Anim | 2018-08-30 | Bug |  | CameraTracker fixed - this wasn't wrapped in the eval manager calls and parallel was breaking the process
SP | r9Anim | r9Anim | 2018-08-10 | Feature |  | Mirror Symmetry is now exposed and handled in the UI such that you can go L>R and R>L. More importantly if you're running a metarig you no longe have to select both left and right indexed objects to mirror when the hierarchy checkbox is off, the matching side objects are found for you | Symmetry and Mirror object handling
SP | r9Anim | r9Anim | 2018-06-18 | Update | SnapTransforms | New processing flags added to allow for "smartBake" and "step" frame processing. New logic allows you to match current objects key times during processing. If smartBakeRef isn't given then the objects being snapped will be inspected for current key times. If it is given then the objects given will be inspected for times instead. | cutkeys=False, smartbake=False, smartBakeRef=[]
SP | r9General | sceneName | 2018-06-13 | Feature | sceneName | New function to return the sceneName regardless of any Maya file load errors that usually block the standard file(q=True, sn=True) call
SP | r9Anim | r9Anim | 2018-01-28 | Feature | AnimationUI > MetaRigs | When dealing with mRigs theres now a new popupmenu thats triggered when you rmb click over the "MetaRoot" button. This presents a menu with all found mRigs in the scene to choose from. It also exposes a new "Auto-Resolved" option that will bind all operations to the rig found from the currently selected. | This is a workflow speedup, saving animators from having to continually set the MetaRoot in the UI. Instead the pose will load onto the rig found from the selected controller.
SP | r9General | decorator | 2018-01-10 | Feature | deleteNewNodes | New decorator that deletes any nodes generated by the function being decorated
SP | r9Anim | snapTransforms | 2017-12-29 | Update | AnimFunctions.snapTransform | New flag added additionalFuncs=[] which allows us to pass in a list of additional function calls to the process. | This allows us to add new functionality whilst only parsing time once, and managing the threading etc
SP | r9Core | r9Core | 2017-12-28 | Bug | FilterNode | Possible to have duplicate nodes in the lists if nodeTypes included shape and transforms | Added extra catches to the lsSearchNodeTypes call
SP | r9Meta | MetaClass | 2017-12-11 | Update | isMetaNodeInherited | Re-written the whole subclass and registry management, added new global var that tracks each classes inheritance map but is able to have the keys looked up in short form rather than full issubclass call | This is to by-opass issue where a class may be instanitated several times during boot-up and from different setups. This was failing our internal developoment code as we have 2 branches and couldn't always check subclasses in the standard manner.
SP | r9Meta | MetaClass | 2017-11-14 | Bug | float3 handling | BUG: mNode.addAttr(attrType='float3') | float3 handling in the addAttr was failing
SP | r9Pose | PoseData | 2017-11-08 | Bug | PoseBlend | The PoseBlender UI was failing to deal with the floatSlider at zero, causing issues blending back to the original pose | Now handled correctly and UI call now handled in a new class in the Pose module
SP | r9Pose | PoseData | 2017-11-08 | Bug | fingerMirrorID_posehandler | The custom filngerMirrorID_poseHandler was failing to handle selection, always forcing the finger load to the whole system | Now handled correctly
SP | r9Pose | DataMap | 2017-10-15 | Feature | World Co-ordinates | The Pose now includes world space data from the API | This will eventually be rolled into the loader also so that data can be loaded in World-Space directly
SP | r9Pose | DataMap | 2017-09-18 | Bug | Maya Units | The load code wasn't dealing with unit conversion, if a pose had been saved in a scene when it was centimeters, buth the scene units had been changed then the pose would fail to load correctly | Handling added for all unit conversions, this uses the sceneUnits stored in the file to convert all linear units.
SP | r9Core | r9Core | 2017-06-12 | Bug | TimeOffset.fromSelected | When using the mRigs flag AND an active filterSettings node with mRig set internally, the code would processs matching nodes from both filters twice | This doubled the offset set when dealing with mRigs
SP | r9Anim | MirrorHierarchy | 2017-05-30 | Update | AnimationUI > Mirror | When Mirroring data we now validate that none of the nodes being processed are constrained, if so we throw a warning | Constrained nodes don't mirror correctly causing issues in the data that are sometimes hard to debug
SP | r9Anim | r9Anim | 2017-05-25 | Update | AnimationUI > MetaRigs | When dealing with mRigs all the hieracrhy checkboxes now process the entire rig, regardless of what controller you have selected | This by-passes users having to always select the Main_Ctrl on the rigs when wanting to copyKeys, copyAttrs etc with hierarchy
SP | r9Anim | r9Anim | 2017-04-28 | Feature | curveModifierContext | now takes an additional flags "processBlanks" that allows us to force the initial undo. | The issue is that calls from the likes of QT don't add named commands to the undoStack
SP | r9Core | r9Core | 2017-04-28 | Update | getBlendTargetsFromMesh | Added new flag "indexes" which will include the indexes back in the returned data | Useful for debugging blendNodes
SP | r9Meta | MetaClass | 2017-04-14 | Bug | nameSpace/nameSpaceFull | BUG: the nameSpace handlers were not returning the correct data, specifically in nested files | Fixed as intended
SP | r9Pose |  | 42826 | Update | poseCompare | Return data and Error prints re-organised to make it easier to debug issues
SP | r9Meta |  | 2017-03-08 | Feature | userinfo | new property to manage "userinfo" on subclasses | This is being used in ProPack to manage and store export and shot data back to the r9Anim systems
SP | r9Meta |  | 2017-02-27 | Feature | MetaClass.attrIsLocked | attr flag now also takes a list | allows you to check the status of multiple attrs in one go. All attrs must be the same else the return is False
SP | r9Core | matchNodeLists | 2017-02-03 | Bug | r9Core.matchNodeLists | We never coded the "metaData" matchMethod! | Added in so that now we can clamp all copy functions to JUST running matching based on the metaData wiring maps
SP | r9Anim | r9Anim | 2017-01-26 | Feature | AnimationUI | Added a new call to r9Core.TimeOffset to allow you to switch the offset value to a 'start at' time by passing in a new arg "start_frm" | The new call also was integrated into the AnimationToolkit under the TimeOffset > Timerange > "ToStart At" checkbox
SP | r9Core | TimeOffset | 2017-01-26 | Bug | r9Core.TimeOffset | Keys range being cut when offsetting animation data backwards was wrong, resulting in dropping the start frame | Fixed and added in the new start_frm feature
SP | Maya Menu's | Timeslider | 2017-01-15 | Feature | Inverse time | Added new inverse animation calls to the timeline menus. Also made the padding and collapse menus capable of binding directly to a given mRig
SP | Maya Menu's | Timeslider | 2017-01-15 | Feature | Timecode added | Timecode management added to the Maya timeline menus | This new menu allows you to modifiy the Maya internal production timecode seen on the timeslider without actually having to push your animations around, so frame 0 can still be represented as 01:00:00:00 if needed
SP | Maya Menu's | GraphEditor - Curve | 2017-01-15 | Feature | Inverse Key Time added | Added a call to allow you to reverse key times around themselves | Allows you to select a bunch of keys and reverse time on them without having to specify a centre pivot, all worked out for you
SP | r9Audio | AudioNode | 2017-01-10 | Update | gatherInfo | Adde a more generic method to gather data on the AudioNode in a consistent manner. This update also lets the inspect call run on multiple audio nodes, propagating multiple detail windows
SP | r9Meta | MetaClass | 2017-01-10 | Bug | __getattribute__ | BUG: any instance of the class was not throwing errors when you tried to call an attr on the instance that didn't exist. | New attr error handling that will throw an error on attrs that don't exist onm the instance or mNode
SP | r9Meta |  | 2017-01-10 | Feature | getMetaRigs | getMetaRigs_fromSelected function added to make it easier to get mRigs from any selected controller on them
SP | r9Meta | MetaClass | 2017-01-06 | Update | __getattribute__ | Added new method catch in the __getattribute__ call to by-pass the issue of dead MetaNodes bailing some of the calls. Also added in a new MetaInstanceError exception so we can catch this more easily | Speeds up the systems and enables you to test .isValid() on an inValid mNode when the scene has been replaced and the mNode and mObject is no longer valid. Prior to this that call would bail if you'd called a new scene after instantiation
SP | r9Anim | r9Anim | 2016-09-20 | Bug |  | Audio ranges being calculated we're based on only comparing that the audios started within the range and ignoring the end, this was causing unexpected audio to get added to the load ranges | _extract_audio now uses ''byRange'' as default NOT ''byRange_start''
SP | r9Audio | Timecode | 2016-09-20 | Bug |  | Timecode EnterUI was only generating the counter from frame 0 and NOT propagating the timecode from the selected frame as it should be | Now functions as expected
SP | r9Audio | importAndActivate | 2016-09-20 | Bug |  | This function was NOT checking when given a path to load, that that audio wasn't already loaded, and in some cases calling a re-load of that audio was crashing Maya | Function now verifies if the audio is already loaded and stops the import if found